## Title Page
Group Number: | 9 | Sprint Number: | 3
eventFindr - User Stories

## Product Backlog
Project Number: | 9
Project Name: | eventFindr
Description: | Provide users with single interface that connects their various event sites like Facebook and Meetup. Users can use our site to easily sort and seach those events for a more simplistic and efficient manner. |  |  | Product Backlog
Team Members: | Alex White, Joshua Weatherford, Tyler Montgomery, Zachary Martin, Kevin Arreola, Pa Pa Oo
Story # | Card Front | Card Back | Assigned To | Comments | Estimated Size (S,M,L) | Estimated Size (Hours) | Estimated Velocity
ST-0 | As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality> |  |  |  |  | (Estimated Size / Estimated Hours)
ST-1 | As a user I need to be able to create login credentials so that I may login to my eventFinder account | User shall be able to create a login name as well as a password | Josh W. | Priority 14 | L | 24
ST-2 | As a user I need to be able to see my Facebook and Meetup events | Use Facebook & Meetup APIs to pull event data for user. Display results | Josh W. | Priority 1 | L | 24
ST-3 | As a user I need to be able to search my events so that I can find what I need from multiple sources | Use site search bar to search for entered terms | Tyler M. | Priority 4 | L | 24
ST-4 | As a user I need to be able to input my interests and preferences for event types. | Use "favourite" to store my interest and preferences for the event types that I am interested | Tyler M. | Priority 3 | S | 6
ST-5 | As a user I need to be able to rate the events so that I can know which is the most popular. | Use "star" logo to choose a rank of the event. ( 5 = highest, 1 = lowest) | Zack M. | Priority 5 | S | 6 | 1
ST-6 | As a user I need to be able to put comments on the events so that everyone can know each other thoughts/feedback on the events " | Add comment function: registered users allow to create comments. | Alex W | Priority 6 | S | 6
ST-7 | As an event provider I can create an event for others to see. | Add create button | Kevin A | Priority 11 | S | 6
ST-8 | As an event provider I can edit my own event so that I can make some changes when needed | Add edit button | Kevin A | Priority 8 | S | 6
ST-9 | As an event provider I can delete my event so that I can take away my event from the list | Add a delete function | Kevin A | Priority 12 | S | 6
ST-10 | As a user I need to be able to see events that around area so that I can see what interest me | Use scroll down button to fit the radius to search the events that I am interested. | Alex W | Priority 10 | M | 12
ST-11 | As a user, I can share events I'll attend/have attended to Facebook | Create "share" button which allow to share the link of the event | Josh W. | Priority 7 | M | 12
ST-12 | As a user, I can link events to my google calendar | Create “add event to calender” button | Josh W. | Priority 9 | M | 12
ST-13 | As a user I need to able to see the description about the event so that I can get more details about the event that I am going | Create additional free text space | Kevin A | Priority 13 | S | 6
ST-14 | As a user I need to be able to delete comments on the events so that any rude comments will be deleted | Add a delete function under "comment" | Tyler M. | Priority 2 | S | 6
ST-15 | As a user, I need to be able to RSVP to events | events should have a RSVP button | Zack M. | Priority 15 | S | 6
ST-16 | As a user, I need to be able to see which events I have RSVP'd to | Create a tab that displays all the events you RSVP | Alex W | Priority 16 | S | 6
ST-17 | As a user, I need to be able to rescind any RSVP I make | Create delete RSVP function | Zack M. | Priority 17 | S | 6
ST-18 | As a user, I need to be able to review my event so that I m able to see how my event look alike | Create a view function | Pa Pa Oo | Priority 18 | S | 6
ST-19 | As a user, I need to be able find events so that I can look into the one I m interested | Create find function | Pa Pa Oo | Priority 19 | M | 12
ST-20 | As a user I need to be able to contact the host so that I can communicate. | User shall be able to leave message to the host. | Pa Pa Oo | Priority 20 | S | 12
|  |  | Story Point Key | Estimated Hours
|  |  | Small | 6
|  |  | Medium | 12
|  |  | Large | 24

## Doing
9
Project Name: | eventFindr
Description: | Provide users with single interface that connects their various event sites like Facebook and Meetup. Users can use our site to easily sort and seach those events for a more simplistic and efficient manner. |  |  | Doing
Team Members: | Alex White, Joshua Weatherford, Tyler Montgomery, Zachary Martin, Kevin Arreola, Pa Pa Oo
Story # | Card Front | Card Back | Estimated Size | Estimated Size (Hours) | Actual Hours | Estimated Velocity Delta | Actual Velocity | Sprint Number | Priority | Assigned To | Comments
ST-12 | As a user, I can link events to my google calendar | Create “add event to calender” button | M | 12 | 8(ongoing) | 1.25 | 0.67 | 2 | Priority 9 | Josh W.
ST - 20 | As a user I need to be able to contact the host so that I can communicate. | User shall be able to leave message to the host. | S | 6 | 3(ONGOING) | 2 | 2 | 2 | Priority 20 | Pa Pa | Created a contact form to contact the host. Need to create database to store all those contact message by attendee. (PaPa)
ST-3 | As a user I need to be able to search my events so that I can find what I need from multiple sources | Use site search bar to search for entered terms | L | 24 | 6(ONGOING) | 1.5 | 1.3 | 2 | Priority 4 | Josh W. | PaPa added search bar, just need to make functional
ST-7 | As an event provider I can create an event for others to see. | Add create link | S | 6 | 2(ONGOINIG) | 1.1 | 1 | 2 | Priority 11 | Kevin A | Created a new event form to fill in. Linking a created event (new) under created events category has not done yet. (PaPa)
ST-15 | As a user, I need to be able to RSVP to events | events should have a RSVP button | S | 6 | 1h33m(Done until ST-7 is done) | 1 | 0.25 | 2 | Priority 15 | Zack M.
ST- 8 | As an event provider I can edit my own event so that I can make some changes when needed | Add edit button | S | 6
ST-9 | As an event provider I can delete my event so that I can take away my event from the list | Add a delete function | S | 6
|  |  | Story Point Key | Estimated Hours
|  |  | Small | 6
|  |  | Medium | 12
|  |  | Large | 24

## Done
Project Number: | 9
Project Name: | eventFindr
Description: | Provide users with single interface that connects their various event sites like Facebook and Meetup. Users can use our site to easily sort and seach those events for a more simplistic and efficient manner. |  |  | Done
Team Members: | Alex White, Joshua Weatherford, Tyler Montgomery, Zachary Martin, Kevin Arreola, Pa Pa Oo
Story # | Card Front | Card Back | Sprint Number | Priority* | Total Estimated Size (S,M,L) | Estimated Size (Hours) | Actual Hours | Estimated Velocity Delta | Actual Velocity Delta by Story | Assigned To | Comments
ST-1 | As a user I need to be able to create login credentials so that I may login to my eventFinder account | User shall be able to create a login name as well as a password | 2 | 14 | L | 24 | 18 | 1.5 | 0.75 | Josh W. | Working on logout option still
ST-2 | As a user I need to be able to see events from sites like meetup and eventful events | Use Facebook & Meetup APIs to pull event data for user. Display results | 3 | 1 | L | 24 | 27 | 1.5 | 1.125 | Josh W. | API mixed with direct link
ST-5 | As a user I need to be able to rate the events so that I can know which is the most popular. | Use "star" logo to choose a rank of the event. ( 5 = highest, 1 = lowest) | 3 | Priority 5 | S | 6 | 12 | 2 | 2 | Zachary Martin | ST-7 must be done before this can be finished.
ST-17 | As a user, I need to be able to rescind any RSVP I make | Create delete RSVP function | 3 | Priority 17 | S | 6 | 1 | 1 | 0.19 | Zack M.
|  |  | Story Point Key | Estimated Hours
|  |  | Small | 6
|  |  | Medium | 12
|  |  | Large | 24

## To Do
Project Number: | 9
Project Name: | eventFindr
Description: | Provide users with single interface that connects their various event sites like Facebook and Meetup. Users can use our site to easily sort and seach those events for a more simplistic and efficient manner. |  |  | TO DO
Team Members: | Alex White, Joshua Weatherford, Tyler Montgomery, Zachary Martin, Kevin Arreola, Pa Pa Oo
Story # | Card Front | Card Back | Sprint Number | Priority | Assigned To | Comments | Estimated Size (SML) | Estimated Size (Hours) | Estimated Velocity Delta
ST-0 | As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality>
ST-4 | As a user I need to be able to input my interests and preferences for event types. | Use "favourite" to store my interest and preferences for the event types that I am interested | 2 | Priority 3 | Tyler M. |  | S | 6
ST-6 | As a user I need to be able to put comments on the events so that everyone can know each other thoughts/feedback on the events " | Add comment function: registered users allow to create comments. | 2 | Priority 6 | Alex W |  | S | 6
ST-8 | As an event provider I can edit my own event so that I can make some changes when needed | Add edit button | 2 | Priority 8 | Kevin A |  | S | 6
ST-9 | As an event provider I can delete my event so that I can take away my event from the list | Add a delete function | 2 | Priority 12 | Kevin A |  | S | 6
ST-10 | As a user I need to be able to see events that around area so that I can see what interest me | Use scroll down button to fit the radius to search the events that I am interested. | 2 | Priority 10 | Alex W |  | M | 12
ST-11 | As a user, I can share events I'll attend/have attended to Facebook | Create "share" button which allow to share the link of the event | 2 | Priority 7 | Josh W. |  | M | 12
ST-13 | As a user I need to able to see the description about the event so that I can get more details about the event that I am going | Create additional free text space | 2 | Priority 13 | Kevin A |  | S | 6
ST-14 | As a user I need to be able to delete comments on the events so that any rude comments will be deleted | Add a delete function under "comment" | 2 | Priority 2 | Tyler M. |  | S | 6
ST-16 | As a user, I need to be able to see which events I have RSVP'd to | Create a tab that displays all the events you RSVP | 2 | Priority 16 | Alex W |  | S | 6
ST-18 | As a user, I need to be able to review my event so that I m able to see how my event look alike | Create a view function | 2 | Priority 18 | Pa Pa Oo |  | S | 6
ST-19 | As a user, I need to be able find events so that I can look into the one I m interested | Create find function | 2 | Priority 19 | Pa Pa Oo |  | M | 12
|  |  | Story Point Key | Estimated Hours
|  |  | Small | 6
|  |  | Medium | 12
|  |  | Large | 24